## Sheet1
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Sheet2
RISK MANAGEMENT LOG
Project Name: |  |  | Cloud Lab
National Center: |  |  | -
Project Manager Name: |  |  | Mostafa
Project Description: |  |  | Create a GUI desktop or web application that educators can use to build and manage a lab in AWS without a need for writing any code.
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
1 | Open | High | Low | Yellow | Current project skill set may not be adequate to complete all project work. The current development team may have previously been using different skill sets than the ones required | If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Project Resources Budget Schedule | Schedule approaches the required start date with no identification of required skill sets. | Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | Find internal resource that meets required skill set or train existing resources | Find resource that meets required skill set through external hiring sources.
2 | Open | High | Low | Yellow | The group does not currently poses the skill set for developing a system that can interface with AWS API's. The groups primary education has come from university which doesn't contain cloud computing. As a result the team will need to learn how to use AWS services in order to complete this project. The training needed to bring the group up to speed will take 8.5 hours per person. | If required skills are not obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Schedule | Schedule approaches the required start date without identification of required skill sets. | Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | Conducting AWS API training. | Conducting AWS API training as soon as possible because no other option exists. The training must occour if the project is to succeded.
3 |  | High | Low | Yellow | The group does not currently poses all the skill needed to developed a system using Django. The groups primary education has come from university which doesn't contain a Django course. As a result the team will need to learn how to use Django in order to complete this project. The training needed to bring the group up to speed will take 8.5 hours per person. | If required skills are not obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Schedule | Schedule approaches the required start date without identification of required skill sets. | Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | Conducting Django training. | Conducting Django training as soon as possible because no other option exists. The training must occour if the project is to succeded.
4 |  | High | Low | Yellow | The group does not currently poses all the skill needed to developed a system using Bootstrap, howvever has partial knowledge. The groups primary education has come from university which doesn't contain a Django course. As a result the team will need to learn the ins and outs of bootstrap in order to complete this project. The training needed to bring the group up to speed will take up to 8.5 hours depending on previous knowledge | Schedule approaches the required start date without identification of required skill sets. | Schedule | Schedule approaches the required start date without identification of required skill sets. | Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | Conducting Bootstrap | Conducting Bootstrap training as soon as possible because no other option exists. The training must occour if the project is to succeded.
5 |  | High | Low | Yellow | Project schedule is not clearly defined or understood | If meetings are not run frequently project misunderstandings may occur and therefore delays and rushing will occur | Schedule | Schedule approaches the required start date without identification without any organisation or planning | Three weeks prior to scheduled start for planning and every week onward | Mitigation | Hold scheduling meetings with the project team so they understand the plan and likelihood of missed tasks is reduced. | Share the plan and go through upcoming tasks at each weekly project progress meeting.
6 |  | High | Low | Yellow | Estimating and/or scheduling errors | If estimations and scheduling errors occur the whole project will be delayed and/or will not have the resources to complete | Project Resources/Schedule | Schedule does not go as planned and delays occur | Prior to scheduled start and all through the project | Mitigation | Escalate to project sponsor Ask sponsor based on what is required (budget or time) | Try and work with what is given and make it as well as possible given the resources Ask sponsor based on what is required (budget or time)
7 |  | High | Low | Yellow | Unresolved project conflicts from each person | If conflicts are not solved quickly or are just left as is, things can escalate | Project Team/sponsor | Conflicts arent resolved in time or at all causing even more issues | Plan and combine ideas and implementation early before the set date | Mitigation | During all team meetings discuss each person's opinion and together pick which one is best | Ask sponsor on the best idea and go with that
8 |  | High | Low | Yellow | Lack of communication | Causes lack of clarity and confusion | Project Team/sponsor | Confusion causing mistakes and having to redo everything or even completely miss sections that needed to be completed | A couple prior to scheduled start date and every meeting/discussion | Mitigation | During all team meetings discuss each section and how it is to be done and confirm through talking to each other or communicating via messsages through their push communication option or asking the sponsor if that is what is meant. Make sure to go through each problem immediately | Set a better communication plan up to ensure this doesn’t happen
9 |  | High | Low | Yellow | Unforseen circumstances | Cause lack of completion based on what has happened or cause massive delays | Project Team/sponsor/Project resources | Issues may occur without any notice within someones life that is unpredictable | As the circumstances come up or prior to if possible | Mitigation | Notify team and sponsors early if possible otherwise as soon as it happens and is causing issues and completing things early helps | Ask for extensions from the sponsor or still try and complete it to the best of their ability if it is not granted and ask for help from the team
10 |  | High | Low | Yellow | Technology Requirements/issues | Cause lack of completion based on what has happened or cause massive delays | Project Resources | Not having techlogical requirements means not being able to complete taks and issues can cause more delays | Four weeks prior to scheduled start date imake sure all tech requirements are met and deal with issues that occur | Mitigation | Always have backups and make sure to check requirements before starting | Us an older backup if needed or use a team members document if shared